## Sheet1
SWEEP CorTom tasks & schedule
Code not started
Main code | Purpose | Tasks remaining | Main coder | Notes | Estimated time for completion | Target date | Code not completed
Code complete but needs further testing, comparison to IDL
cortom.py | COR2 data download | Testing on larger date ranges | Chien | This will need adaptation for use on Met Office systems |  | Done | Code complete and tested
secchi_prep.py | Calibration | COR2_WARP | Huw | Huw to investigate and test. cor2_warp_huw |  | 2021-11-19
pb_calibrate_secchi.py | Wrapper for secchi_prep, further processing & coordinate transform of data | Finish code | Chien | Need to write to JSON save files. Need to test. |  | 2021-11-19
timerange2datacube | Reads in files created and saved by pb_calibrate_secchi, and concatenates in datacube | Finish code | Chien | May need to split to smaller functions. |  | 2021-11-22
tomo_prep_data | Takes datacube from timerange2datacube, and reduces to distance range of interest, some further processing. Calls tomo_make_geom | Finish code | Chien |  |  | 2021-11-22
tomo_make_geom | Called by tomo_prep_data, creates various arrays of coordinates in prep for tomography | Finish code | Huw | Need to test on other dates/files. |  | 2021-11-22
tomo_prep_sph | Create spherical harmonic model for tomography |  | Huw |  |  | 2021-12-13
tikhonov_opt_tomo | First step in inversion |  | Huw/Chien/Ed |  |  | 2021-12-13
tikhonov_search_tomo | Second step in inversion |  | Huw/Chien/Ed |  |  | 2021-12-13
tomo_data_2019 | Main tomography code that calls all other codes from pb_calibrate_secchi through to the inversions |  | Chien |  |  | 2021-12-13
tomo_finescale | Takes tomography result and narrows certain density structures, refines match to data |  | Huw/Chien |  |  | 2021-01-17
All tomography codes as single package |  |  | Chien (python) & Huw (IDL) | Running all codes as single package on certain dates, compare output to IDL, extensive testing |  | 2021-12-20
Error logging |  |  | Chien/Huw
Code documentation |  |  | Chien & Huw |  |  | 2021-01-17